## Planning Timeline
WMI Micro-Grant Planning Timeline
Project Title:
Applicant Name:
Project Stages: Planning, Fundraising, Measurement & Evaluation, Implementation, Program Follow-Up, Program Reporting
Project stages have been added to the timeline below. However, you are expected to expand these sections to represent all of the activities you plan to undertake with your project/idea.
Note: Selected Micro-Grant applications will receive funding beginning in February 2019. Plan your activities and completion dates in accordance.
Project Stage | Task Description | Responsible Person | Started on (DD/MM/YYYY) | Completion Due On (DD/MM/YYYY) | Result of the Task Completed
Planning
. . .
. . .
. . .
. . .
Fundraising
. . .
. . .
. . .
. . .
Measurement & Evaluation
. . .
. . .
. . .
. . .
Implementation
. . .
. . .
. . .
. . .
Program Follow-Up
. . .
. . .
. . .
. . .
Program Reporting
. . .
. . .
. . .
. . .

## Example Planning Timeline
WMI Micro-Grant Planning Timeline
Project Title: Expansion of Rabbitry Business
Applicant: Mark Twins
Note: These project stages are fictional and do not represent the full complexity WMI expects to see for an application. This example has been created to demonstrate how to utilize the template.
Project Stage | Task Description | Responsible Person | Started on (DD/MM/YYYY) | Completion Due On (DD/MM/YYYY) | Result of the Task Completed
Planning | Contact rabbit breeders and renegotiate and confirm prices and availability for purchase for a sale in mid-February | Mark | 2017-09-15 | 2017-09-20 | Final price, pick-up date and delivery scheduled.
Planning | Redefine a mating schedule, birth estimates and sale scheme | Mark & Abby | 2017-09-20 | 2017-09-23 | Completed plan for breeding, births and sales keeping in mind that not all pregnancies or live births will be successful in our estimates.
Planning | Contact local veterinarian to reconfirm reduced payment agreement for monthly services | Abby | 2017-09-20 | 2017-09-23 | Provide the most accurate budget estimates for this expense.
Planning | Develop materials and monthly activity plan for youth | Mark & Abby | 2017-10-15 | 2017-11-15 | An initial 5-months of curriculum will be developed to teach youth about starting small livestock businesses.
Planning | Develop training schedule | Mark & Abby | 2017-10-15 | 2017-11-15 | A detailed training schedule with defined topics for each youth group meeting.
Planning | Collect all in-kind donations of supplies | Mark | 2018-01-20 | 2018-01-25 | First month's hay and 10 used hutches are on site.
Planning | Purchase construction supplies | Mark | 2018-02-15 | 2018-02-18 | Construction materials are on site and ready to be used.
Planning | Contract with a construction laborer to assist with building hutches | Mark | 2018-02-01 | 2018-02-01 | Confirmed worker, his ability to bring the needed tools and date for construction to take place.
Fundraising | Receive notice of award decision from WMI | Mark | 2018-01-01 | 2018-01-01 | Receive notice of expected funds.
Fundraising | Provide all final documents to WMI for MG funding | Mark | 2018-01-01 | 2018-01-14 | Complete funding responsibilities.
Fundraising | Receive notice of award decision from Small Farmers Initiative and update WMI | Mark | 2018-01-01 | 2018-01-01 | Receive notice of expected funds.
Fundraising | Receive notice of award decision from Rotary International and update WMI | Mark | 2018-01-01 | 2018-01-01 | Receive notice of expected funds.
Measurement & Evaluation | Create survey to measure current knowledge of small business management for youth involved in the educational component of the project | Mark | 2017-11-15 | 2017-11-20 | Ten question questionnaire aligned with the developed training materials.
Measurement & Evaluation | Review survey with WMI staff and create a final version | Mark & WMI | 2017-11-20 | 2017-11-27 | Receive formal feedback and plan for redesign.
Measurement & Evaluation | Explain and implement survey at an educational meeting with the youth | Mark | 2/30/2018 | 2/30/2018 | Initial survey implemented and data collected.
Implementation | Host introductory meeting to explain the opportunity, objectives, goals and responsibilities for those who participate | Mark & Abby | 2./30/2018 | 2/30/2018 | Gain involvement and record names of those who wish to continue learning more.
Implementation | Recruit 10 unemployed youth (18-25 years old) to participate | Mark, Abby, Baptist Church Pastor | 2018-01-15 | 2018-01-15 | 10 youth recruited and 5 additional youth identified if the original participants do not fulfil the requirements of participation. Collection of names, family background, education background, employment background and contact information.
Implementation | Clean current shed space to make room for 30 additional hutches | Mark & Youth | 2018-01-20 | 2018-01-21 | Introduce youth to the site and prepare for housing the new rabbits.
Measurement & Evaluation | Implement the same survey with the youth | Mark | 2018-06-01 | 2018-06-01 | Second phase of survey implemented and data collected.
Measurement & Evaluation | Review and create statistics showing the difference in responses from the initial and the second survey implementation. | Mark | 2018-06-01 | 2018-06-04 | Showcase and share the data "story" for involved youth, funders, supporters and to assist with future program development.
Measurement & Evaluation | Seek WMI assistance on how to best represent and share these results | Mark & WMI | 2018-06-05 | 2018-06-10 | Improve ability to showcase and share the data "story" for involved youth, funders, supporters and to assist with future program development.
Program Follow-Up | Review matching schedule, births/deaths, production and sales | Mark, Abby & Veterinary | 2018-04-01 | 2018-04-07 | Improve vitality of animals to reach better production results.
Program Reporting | Begin working on report to meet WMI requirements | Mark | 2018-04-15 | 2018-04-25 | Complete report following the guidelines and exceptional photographs supporting three-months worth of project progress.
Program Reporting | Submit WMI Three-Month Report | Mark | 2018-05-01 | 2018-05-01 | Met program deadline.